## project
[55 empty] | PCB released to fab | [7 empty] | PCB back for assembly
Project Planner - Ashwathama
[8 empty] | Period Highlight: |  |  |  |  | 35 | [6 empty] | Actual | [8 empty] | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Self Checkout Shopping Cart |  | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT |  | August 26th |  |  | September 1st | [5 empty] | September 7th | [6 empty] | September 14th | [6 empty] | September 21st | [6 empty] | September 28th |  |  | October 1st | [30 empty] | November 1st | [29 empty] | December 1st | [16 empty] | Project Demos
ACTIVITY |  | START | DURATION | START | DURATION | COMPLETE |  | PERIODS
| Lead | [5 empty] | Comments | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116
Use Case Selection | Siddhant Jajoo | 5 | 1 | 5 | 1 | 100%
Project Proposal - I | Satya , Deepesh, Siddhant | 8 | 1 | 9 | 1 | 100%
Altium Hands-On | Satya , Deepesh, Siddhant | 9 | 7 | 9 | 7 | 100%
Processor Selection | Deepesh Sonigra | 11 | 1 | 11 | 1 | 100%
Sensor Selection | Satya Mehta | 13 | 1 | 14 | 1 | 100%
Radio Selection - NFC | Siddhant Jajoo | 14 | 1 | 14 | 1 | 100%
Android Environment Setup | Siiddhant Jajoo | 15 | 1 | 15 | 1 | 100%
Project Proposal - II | Satya, Deepesh, Siddhant | 16 | 2 | 16 | 2 | 100%
Power Requirement Calculations | Siddhant , Deepesh | 18 | 2 | 18 | 1 | 100%
Power Management IC Selection | Siddhant, Deepesh | 18 | 2 | 19 | 1 | 100%
Android Basic Template | Deepesh Sonigra | 20 | 2 | 20 | 2 | 100%
Schematic Design - Power | Deepesh Sonigra | 22 | 21 | 22 | 24 | 100%
Schematic Design - MCU | Siddhant Jajoo | 21 | 21 | 22 | 25 | 100%
Schematic Design - Radio | Satya Mehta | 21 | 21 | 21 | 22 | 100%
Firmware Development Board-BLE | Satya, Siddhant, Deepesh | 24 | 7 | 24 | 9 | 100%
Firmware Developmen Board-NFC | Siddhant, Satya | 24 | 7 | 25 | 5 | 100%
Schematic Integration | Satya, Deepesh, Siddhant | 30 | 5 | 35 | 5 | 100%
PCB Layout Design | Satya, Deepesh, Siddhant | 35 | 10 | 45 | 10 | 100%
Android App- Bluetooth Capability | Deepesh Sonigra | 45 | 7 | 52 | 0 | 30%
Barcode Sensor Integration | Siddhant Jajoo | 45 | 2 | 47 | 0 | 20%
Exploring AWS and Setting Environment | Satya Mehta | 45 | 7 | 45 | 4 | 100%
Integration BLE-NFC | Siddhant Jajoo | 47 | 5 | 61 | 0 | 0%
Android App Wifi Capability | Deepesh Sonigra | 53 | 5 | 65 | 0 | 0%
Devloping Database For Item Scanning | Siddhant Jajoo | 53 | 5 | 0 | 0 | 0%
PCB Soldering and Component assembly | Satya Mehta | 58 | 2 | 0 | 0 | 0%
PCB Testing and Debugging | Satya Mehta | 60 | 5 | 0 | 0 | 0%
Firmware Testing Phase I -BLE | Deepesh Sonigra | 65 | 4 | 0 | 0 | 0%
Firmware Testing Phase I -NFC | Siddhant Jajoo | 70 | 5 | 0 | 0 | 0%
System Integration | Satya, Deepesh, Siddhant | 77 | 14 | 0 | 0 | 0%
Load Power Testing and Debugging | Satya, Deepesh | 91 | 2 | 0 | 0 | 0%
Android AWS Software Development | Deepesh Sonigra | 91 | 4 | 0 | 0 | 0%
System and App Integration | Satya, Siddhant | 93 | 2 | 0 | 0 | 0%
Full System Testing | Satya, Deepesh, Siddhant | 95 | 2 | 0 | 0 | 0%
Final Integration - Ashwathama | Satya, Deepesh, Siddhant | 97 | 5 | 0 | 0 | 0%
Demo Testing | Satya, Deepesh, Siddhant | 102 | 3 | 0 | 0 | 0%
Future Goal Implementations | Satya, Deepesh, Siddhant | 105 | 5 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%